## V1 (1)
Project Development and Completion Tracker
Porject ID: Obsidian Circuit
Project Start Date: 07-08-2024 Project End Date:21-11-2024
Project Description: Obsidian Circuit is a cutting-edge cyber triage and incident response tool that combines real-time analysis of files, networks, and logs with AI/ML-driven incident prioritization and decentralized blockchain for secure data storage, providing a comprehensive solution for digital forensic investigations.
| Name of Team member | Task
Project Obsidian Circuit Team Members | Aryan Dsouza | Documentation
| Kathan Somani | Ideation & Frontend
| Roque Martins | Blockchain Integration & Backend
| Soham Jagtap | Frontend & Backend Integration
Task1: | Data Collection & Analysis: Implement mechanisms to collect and analyze file, network, and log data for indicators of compromise (IOCs).
Task2: | AI/ML Integration: Integrate artificial intelligence and machine learning algorithms to prioritize incidents and suggest responses.
Task3: | Blockchain Integration: Incorporate decentralized blockchain for secure, high-speed data storage with encryption and backup features.
Task4: | User Interface & Alerts: Develop an intuitive dashboard for users to view and manage investigations, including real-time notifications for critical incidents.
Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Data Collection ,Analysis, Documentation | Gather and analyze files for threat detection and classification. | Complete | Aryan , Soham, Kathan | 2024-08-07 | 2024-08-15 | 2024-08-07 | 2024-08-15 | 100%
AI/ML Integration | Research AI/ML models for detecting and classifying cyber threats. | Partially Complete | Roque ,Aryan | 2024-08-15 | 2024-08-30 | 2024-08-15 | 2024-08-30 | 60%
Partial
Feasibility & Viability | Feasibility & Cost Cutting | Complete | Kathan , Aryan | 2024-08-20 | 2024-08-25 | 2024-08-20 | 2024-08-25 | 100%
Blockchain Integration & Backend | Backend Designing |  | Soham ,Kathan | 2024-08-30 | 2024-09-20 | 2024-08-30 | 2024-09-20 | 100%
| Blockchain Working & Backend | Complete | Roque, Soham | 2024-09-20 | 2024-10-10 | 2024-09-20 | 2024-10-10 | 100%
Frontend & Prototyping | Website Design | Complete | All Team Members (Lead -Roque) | 2024-10-10 | 2024-10-30 | 2024-10-10 | 2024-10-30 | 100%
| Designing Prototype | Complete | All Team Members | 2024-10-30 | 2024-11-20 | 2024-10-30 | 2024-11-20 | 100%

## Version 2 (1) (hidden)
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%